## AIDCORE - Project Plan
PROJECT: AIDCORE - AI Driven Customer Operations & Realtime Engagement
[5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project start date: | 2024-05-27 |  |  |  |  | June | [34 empty] | July
Scrolling increment: | 5 | time axis 2024-06-01 to 2024-07-26
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-06-01 to 2024-07-26
INTERACTIVE EXPERIMENTATION | Tolegate1
Data Prep | Milestone | TBD | 0% | 2024-05-27 | 5
Feature Engg | Milestone | TBD | 0% | 2024-06-01 | 5 | bar: 2024-06-01 to 2024-06-05
Model Design & Training | Milestone | TBD | 0% | 2024-06-06 | 5 | bar: 2024-06-06 to 2024-06-10
Model Evaluation | Milestone | TBD | 0% | 2024-06-11 | 5 | bar: 2024-06-11 to 2024-06-15
Prototype Testing | Milestone | TBD | 0% | 2024-06-16 | 5 | bar: 2024-06-16 to 2024-06-20
CI/CD Setup | Tolegate2
Fast API | Milestone | TBD | 0% | 2024-06-21 | 2 | bar: 2024-06-21 to 2024-06-22
Setup CI/CD on Git | Milestone | TBD | 0% | 2024-06-23 | 2 | bar: 2024-06-23 to 2024-06-24
Testing Dataset change | Milestone | TBD | 0% | 2024-06-25 | 2 | bar: 2024-06-25 to 2024-06-26
Testing with updated Model | Milestone | TBD | 0% | 2024-06-27 | 2 | bar: 2024-06-27 to 2024-06-28
INTERACTIVE EXPERIMENTATION | Tolegate3 | TBD
Model Staging | Milestone | TBD | 0% | 2024-06-29 | 3 | bar: 2024-06-29 to 2024-07-01
Automated Testing | Milestone | TBD | 0% | 2024-07-02 | 3 | bar: 2024-07-02 to 2024-07-04
Model Release | Milestone | TBD | 0% | 2024-07-05 | 3 | bar: 2024-07-05 to 2024-07-07
Online Experimentation | Milestone | TBD | 0% | 2024-07-08 | 3 | bar: 2024-07-08 to 2024-07-10
Live Product | Milestone | TBD | 0% | 2024-07-11 | 3 | bar: 2024-07-11 to 2024-07-13

## Weekly Progress Goals
Weekly Progress Goals
Week | Date | Progress Goal
Week 1 | 2024-06-23 | Present the working prototype using Google Colab and Visual Studio Code
Week 2 | 2024-06-30 | Present the CI/CD on Git and working Prototype using Fast API/Gradio/Streamlit
Week 3 | 2024-07-07 | Present working Model using AWS/Cloud9/EC2
Week 4 | 2024-07-14 | Final Live product with all feature
Formulas:
Date = [Date, row above]+7

## Team Members
S.No. | Team members | Email ID
1 | Debolina Mahapatra | mahapatradebolina@gmail.com
2 | Jatin Goyal | Jt1491995@gmail.com
3 | Jyotirmoy Patra | jyotirmoy.nsec@gmail.com
4 | Neelesh Kumar Boddu | neeleshkumar7@gmail.com
5 | Pankaj kumar soni | soni.pankajkumar@gmail.com
6 | Paramashiva B M | parama86@gmail.com
7 | Puja Chakraborty | pujachakraborty1810@gmail.com
8 | Sajjan Sagar | sajjan.sagar@gmail.com
9 | Shaik Athahar Nawaz | Shaikn@microsoft.com
10 | Shiva C R | shivacr242@gmail.com
11 | Shrikantha Prabhu | shrikantha@shrikanthaprabhu.com